## Bug Tracker
Bug ID | Date Logged | Reported By | Original Description (Jessica's words) | Enhanced Description (refined understanding) | Root Cause | Resolution / Fix Applied | Status | Reference (commit / PR / files)
BUG-001 | 2026-06-30 | Jessica | The reminder email that's supposed to be sent the morning of class isn't sending. | The daily morning-of class reminder (the sendClassReminders function, scheduled ~7 AM Pacific) never fired in production, so registered students got no day-of reminder. The reminder code itself was correct — the problem was that the scheduled job running it didn't exist. | sendClassReminders was newly added in the schedule-admin commit (be01821). Time-driven triggers in Apps Script are NOT created by deploying/pasting code — they only exist once setupTriggers() is run. After the deploy, setupTriggers() had not been re-run, so the daily reminder trigger was never installed and the function never executed. (Confirmed against Jessica's recollection that the one-time trigger setup may not have been re-run after deploy.) | Re-ran setupTriggers() from the Apps Script editor to install the sendClassReminders daily trigger (Day timer, ~7–8 AM PT) along with the other time-driven triggers. No code change required — reminder logic was already sound. Verify via Apps Script → Triggers (sendClassReminders listed) and → Executions (next morning run shows Completed). | Fixed | Operational fix (no code change): setupTriggers() in google-apps-script.js; function added in commit be01821.
BUG-002 | 2026-06-30 | Jessica | The Zoom link that's supposed to be sent to a student who signs up the same day isn't working. The case that failed was a student signing up 33 minutes before class start. | A student signing up shortly before an online class (roughly 30–35 minutes out) received no Zoom link — not in the confirmation email and not from the periodic invite. The specific "33 minutes" wasn't special; it landed in a dead zone between two different senders that were supposed to cover the link delivery. | Two code paths deliver the link. The periodic sendMeetInvites trigger emails it during the 25–35 min pre-class window, then sets a meet_sent_ flag and skips anyone who signs up afterward. The inline confirmation-email path only attached a link when the class was ≤30 min away. A signup at 30–35 min fell in the gap: too late for the periodic send (already flagged sent), too early for the inline path. Compounding it, the inline path also set meet_sent_ itself, and sendMeetInvites always created a brand-new meeting instead of reusing the cached one. | Widened the inline confirmation window to 40 min (LATE_SIGNUP_WINDOW_MIN) so it overlaps the periodic 25–35 min window with margin; stopped the inline path from setting meet_sent_ (that flag now means only "bulk email sent to all students"); made sendMeetInvites reuse a cached meeting instead of creating a duplicate. Redeployed the corrected script. | Fixed | commit 53f1b83 / PR #1; google-apps-script.js (checkAndCreateMeetForLateSignup, sendMeetInvites).
BUG-003 | 2026-06-30 | Jessica | Every email now has a weird character. The subject shows "Yoga with Jessica ‚Äî Sign-Up Confirmation"; the sign-up notification body shows "Sunday Evening — Online via Zoom ‚Äî Sunday, June 28, 2026 (online)"; and the Zoom-link-ready email shows "Class is starting soon ‚Äî join here:". | Em-dashes (and curly apostrophes) that were hardcoded as literal characters in the script's email strings rendered as Mac-Roman mojibake (‚Äî). Tellingly, an em-dash coming from sheet data — e.g. the one inside the class name "Sunday Evening — Online via Zoom" — rendered correctly, so only the literal multibyte characters in the source code were affected, not data-sourced text. | The Apps Script is deployed by copy-pasting the file into the Apps Script editor, which re-decoded the raw UTF-8 em-dash bytes (E2 80 94) as Mac Roman, producing "‚Äî". Sheet-sourced text was unaffected because it round-trips as proper UTF-8. | Made every user-facing string paste-proof by replacing raw multibyte characters with ASCII-safe forms: \u2014 in subjects/plaintext/split-keys/regexes, &mdash; and &rsquo; in HTML bodies, and \u26A0 for the admin emoji. Also hardened the schedule seed labels (the Schedule↔Sign-Ups join key) and the 'YES — Accepted' waiver default written to the sheet. Mirrored the fixes into the test backend. Requires redeploying the corrected script (done). | Fixed | commit 53f1b83 / PR #1; google-apps-script.js and google-apps-script-test.js.